## Sheet1 (hidden)
|  | May |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov
|  | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05
CE Phase 2 Inbound |  | 2022-05-23: Analysis; 2022-05-30: Analysis; 2022-06-06: Design; 2022-06-13: Design; 2022-06-20: Design; 2022-06-27: Design; 2022-07-04: Dev&UT; 2022-07-11: Dev&UT; 2022-07-18: SIT; 2022-07-25: SIT; 2022-08-01: UAT; 2022-08-08: UAT; 2022-08-15: Go-Live; 2022-08-22: Hyper Care; 2022-08-29: Hyper Care; 2022-09-05: Hyper Care
As-Is Analysis & Simplification
Technical Design
Development and UT
SIT
UAT
Go-Live(Deployment)
Hyper Care
CE Phase 2 DM |  |  | Analysis | Analysis | Analysis | Analysis | Design | Design | Design | Dev&UT | Dev&UT | Dev&UT | SIT | SIT | SIT | UAT | UAT | Go-Live | Hyper Care | Hyper Care | Hyper Care
As-Is Analysis & Simplification
Technical Design
Development and UT
SIT
UAT
Go-Live(Deployment)
Hyper Care
CE Phase 2 Outbound |  |  |  |  | Analysis | Analysis | Analysis | Analysis | Design | Design | Design | Dev&UT | Dev&UT | Dev&UT | Dev&UT | Dev&UT | SIT | SIT | SIT | UAT | UAT | UAT | Go-Live | Parallel Run | Parallel Run | Parallel Run | Cut Over | Hyper Care | Hyper Care | Hyper Care
As-Is Analysis & Simplification
Technical Design
Development and UT
SIT
UAT
Go-Live(Deployment)
Parallel Run
Cutover
Hyper Care
CE Phase 2 Report |  |  |  |  | Analysis | Analysis | Design | Design | Design | Dev&UT | Dev&UT | Dev&UT | Dev&UT | Dev&UT | Dev&UT | SIT | SIT | SIT | UAT | UAT | UAT | Go-Live | Hyper Care | Hyper Care | Hyper Care
As-Is Analysis & Simplification
Technical Design
Development and UT
SIT
UAT
Go-Live(Deployment)
Parallel Run
Cutover
Hyper Care
CE Phase 2 Legcy Teradata Decouple |  | 2022-09-05: Analysis; 2022-09-12: Analysis; 2022-09-19: Design; 2022-09-26: Design; 2022-10-03: Dev&UT; 2022-10-10: Dev&UT; 2022-10-17: SIT; 2022-10-24: SIT; 2022-10-31: UAT; 2022-11-07: UAT; 2022-11-14: Cut Over; 2022-11-21: Hyper Care; 2022-11-28: Hyper Care; 2022-12-05: Hyper Care

## Sheet2 (hidden)
|  | May |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov
|  | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07
CE Phase 2 Inbound | bar: 2022-05-23 to 2022-06-13
As-Is Analysis & Simplification
Technical Design
Development and UT
SIT
UAT
Go-Live(Deployment)
Hyper Care
CE Phase 2 DM
As-Is Analysis & Simplification
Technical Design
Development and UT
SIT
UAT
Go-Live(Deployment)
Hyper Care
CE Phase 2 Outbound
As-Is Analysis & Simplification
Technical Design
Development and UT
SIT
UAT
Go-Live(Deployment)
Parallel Run
Cutover
Hyper Care
CE Phase 2 Report
As-Is Analysis & Simplification
Technical Design
Development and UT
SIT
UAT
Go-Live(Deployment)
Parallel Run
Cutover
Hyper Care
CE Phase 2 Legcy Teradata Decouple

## Project Plan
|  | Medical Report | Aug | [5 empty] | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan
|  |  | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
|  | GMA China Value & KPI Report | 2022-08-01: Analysis; 2022-08-22: Design; 2022-08-29: Design; 2022-09-05: Dev&UT; 2022-09-12: Dev&UT; 2022-09-19: Dev&UT; 2022-09-26: Dev&UT; 2022-10-10: `SIT; 2022-10-17: `SIT; 2022-10-24: UAT; 2022-10-31: UAT; 2022-11-07: Go-Live; 2022-11-14: Hyper Care; 2022-11-21: Hyper Care; 2022-11-28: Hyper Care; 2022-12-05: Hyper Care
|  | WeChat Work 研而有信 Reports | 2022-08-29: Analysis; 2022-09-05: Analysis; 2022-09-12: Design; 2022-09-19: Design; 2022-09-26: Dev&UT; 2022-10-10: Dev&UT; 2022-10-17: Dev&UT; 2022-10-24: SIT; 2022-10-31: SIT; 2022-11-07: UAT; 2022-11-14: UAT; 2022-11-21: Go-Live; 2022-11-28: Hyper Care; 2022-12-05: Hyper Care
Phase | Name
GMA China Value & KPI Report
Analysis | Charles Li | [29 empty] | 15 | bar: 2022-08-01 to 2022-08-15
| Vicky Zhuang | [29 empty] | 10 | bar: 2022-08-08 to 2022-08-15
| Polina Peng | [29 empty] | 10 | 35 | bar: 2022-08-08 to 2022-08-15
Design | Charles Li |  | 2022-08-22: 1; 2022-08-29: 0.5 |  | 7.5 | 10
| Polina Peng | [29 empty] | 10 | bar: 2022-08-22 to 2022-08-29
| Vicky Zhuang | [29 empty] | 10 | bar: 2022-08-22 to 2022-08-29
Development | Doris Ding |  | 2022-08-15: 1; 2022-08-22: 1; 2022-08-29: 1; 2022-09-05: 1; 2022-09-12: 1; 2022-09-19: 1; 2022-09-26: 0.5; 2022-10-10: 0.5; 2022-10-17: 0.5; 2022-10-24: 0.5; 2022-10-31: 0.5 |  | 42.5
| Vicky Zhuang |  | 2022-09-05: 1; 2022-09-12: 1; 2022-09-19: 1; 2022-09-26: 1; 2022-10-10: 0.5; 2022-10-17: 0.5 |  | 25
| Becky Tan | [29 empty] | 30 | 30 | bar: 2022-09-05 to 2022-09-26; 2022-10-10 to 2022-10-17
SIT | Xiaolin Liu | [29 empty] | 10 | bar: 2022-09-26; 2022-10-10
| Cassie Jiang | [29 empty] | 10 | 20 | bar: 2022-09-26; 2022-10-10
UAT | Polina Peng | [29 empty] | 15 | bar: 2022-10-17 to 2022-10-31
| Xiaolin Liu | [29 empty] | 15 | bar: 2022-10-17 to 2022-10-31
| Cassie Jiang | [29 empty] | 10 | 20 | bar: 2022-10-24 to 2022-10-31
WeChat Work 研而有信 Reports
Analysis | Charles Li |  | 2022-08-29: 0.5; 2022-09-05: 1 |  | 7.5
| Polina Peng | [29 empty] | 15 | bar: 2022-09-05 to 2022-09-19
Design | Charles Li | [29 empty] | 10 | 15 | bar: 2022-09-12 to 2022-09-19
Development | Charles Li | [29 empty] | 40 | bar: 2022-09-26; 2022-10-10 to 2022-11-21
| Doris Ding |  | 2022-09-26: 0.5; 2022-10-10: 0.5; 2022-10-17: 0.5; 2022-10-24: 0.5; 2022-10-31: 1; 2022-11-07: 1; 2022-11-14: 1; 2022-11-21: 1 |  | 30
| Vicky Zhuang |  | 2022-10-10: 0.5; 2022-10-17: 0.5; 2022-10-24: 1; 2022-10-31: 1; 2022-11-07: 1; 2022-11-14: 1; 2022-11-21: 1 |  | 30
| Becky Tan | [29 empty] | 20 | 50 | bar: 2022-10-24 to 2022-11-14
SIT | Xiaolin Liu | [29 empty] | 5 | bar: 2022-10-31
| Cassie Jiang | [29 empty] | 5 | 9 | bar: 2022-10-31
UAT | Polina Peng | [29 empty] | 10 | bar: 2022-11-07 to 2022-11-14
| Xiaolin Liu | [29 empty] | 15 | bar: 2022-11-07 to 2022-11-21
| Cassie Jiang | [29 empty] | 15 | 15 | bar: 2022-11-07 to 2022-11-21
Support（SIT,UAT,Hyper Care）
| Polina Peng | [29 empty] | 20 | bar: 2022-09-26; 2022-10-10 to 2022-10-17; 2022-10-31
Doris Ding | bar: 2022-11-28 to 2022-12-19
| Vicky Zhuang | [29 empty] | 20 | bar: 2022-11-28 to 2022-12-19
Total |  |  | 1 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 7 | 0 | 7 | 7 | 7 | 10.5 | 7 | 7 | 5 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462.5

## Project Detail Plan
Report | Phase | Task | Sub-task | Status | Start Date | End Date | Assignee | Reviewer | Deliverable | Comment
Environment | Environment | Schema |  | Done | 2022-08-09 | 2022-08-26 | Charles | Charles | New Schema
|  | Matillion |  | Done | 2022-08-09 | 2022-08-26 | Charles | Charles | New Matillion
|  | Account |  | Done | 2022-08-09 | 2022-08-26 | Charles | Roy
|  | Solution Review |  | In Progress | 2022-08-09 | 2022-09-16 | Charles | Joey | Solution Proposal
|  | Solution POC |  | On Hold | 2022-08-09 | 2022-09-16 | Charles | Joey
GMA China Value and KPI Report | Analysis | Standard Report | Field Medical Report (Value + KPI) | In Review | 2022-08-09 | 2022-08-26 | Polina | Lion | Document Review
|  |  | MIR Value Reprot | Done | 2022-08-09 | 2022-09-08 | Polina | Lion | Document Review
|  | Self-Service & Row Data | Field Medical Report (Value + KPI) | In Review | 2022-08-09 | 2022-09-02 | Charles | Lion | Document Review | Master Data(Existing) + DFS Org& Manual data (Design) + CRM Call &Event /eEvent PR (data_20220712) + Target Physician (All Fields)
|  |  | MIR Value Reprot | In Review | 2022-08-09 | 2022-09-02 | Charles | Lion | Document Review | Master Data(Existing) + DFS manual Data(Design) + Medical Inquiry(All Fields) 业务提出要增加字段
|  |  | Sent Message | In Review | 2022-08-09 | 2022-09-02 | Charles | Lion | Document Review | Master Data(Existing) + DFS Org(Design) + Sent Message (All Fields & Depends Common) 等待Lion KT
| Design | Standard Report Mockup | Field Medical Report (Value + KPI) | Done | 2022-08-22 | 2022-09-09 | Polina | Lion | Mockup
|  |  | MIR Value Reprot | Done | 2022-08-22 | 2022-09-09 | Polina | Lion | Mockup
|  | Inbound Degisn | Inbound Interface | In Progress | 2022-08-22 | 2022-09-09 | Charles | Lion | Draft Design Document
|  | DWH & DM Design & Self-Service | Field Medical Report (Value + KPI) | Done | 2022-08-22 | 2022-09-16 | Charles | Lion | Draft Design Document | 设计已完成，文档未完成
|  |  | MIR Value Reprot | Done | 2022-08-22 | 2022-09-16 | Charles | Lion | Draft Design Document
|  |  | Field Medical Self-Service POC | In Review | 2022-09-05 | 2022-09-13 | Polina,Vicky | Lion | POC
|  |  | Send Message Self-Service POC | In Review | 2022-09-05 | 2022-09-19 | Polina,Vicky | Lion | POC
|  |  | MIR Self-Service POC | Done | 2022-09-05 | 2022-09-09 | Polina,Vicky | Lion | POC
|  |  | Send Message | In Review | 2022-08-22 | 2022-09-16 | Charles | Lion | Draft Design Document
| Development | DWH & DM | Field Medical Standard Report | In Review | 2022-09-05 | 2022-09-21 | Doris,Becky | Charles,Lion | Code & UT
|  |  | Field Medical Self-Service | In Review | 2022-09-05 | 2022-09-21 | Doris,Becky | Charles,Lion | Code & UT
|  |  | MIR Value Standard Report | In Review | 2022-09-13 | 2022-09-16 | Doris,Becky | Charles,Lion | Code & UT
|  |  | MIR Self-Service | In Review | 2022-09-13 | 2022-09-20 | Doris,Becky | Charles,Lion | Code & UT
|  |  | Sent Message Self-Service | In Review | 2022-09-22 | 2022-09-30 | Doris,Becky | Charles,Lion | Code & UT
|  | Report | Field Medical KPI Standard Report | In Review | 2022-09-14 | 2022-09-20 | Vicky | Lion | Code & UT
|  |  | MIR Value Standard Reprot | In Review | 2022-09-21 | 2022-09-23 | Vicky | Lion | Code & UT
|  |  | Field Medical Self-Service | In Review | 2022-09-26 | 2022-09-28 | Vicky | Lion | Code & UT
|  |  | MIR Self-Service | In Review | 2022-09-29 | 2022-09-30 | Vicky | Lion | Code & UT
|  |  | Sent Message Self-Service | In Review | 2022-09-26 | 2022-09-30 | Vicky | Lion | Code & UT
|  | Inbound | Inbound Interface | To Do | 2022-09-30 | 2022-10-07 | Doris,Becky | Charles,Lion | Code & UT
| SIT | Test case design |  | In Progress | 2022-10-08 | 2022-10-11 | Xiao Lin | Lion | Test Case
|  | Test data preparation |  | To Do | 2022-10-08 | 2022-10-10 | Doris | Lion | Test Data
|  | SIT Deployment(IQ and request for RMO) |  | To Do | 2022-10-11 | 2022-10-12 | Doris | Lion | Deployment to Test Environment
|  | Test case execution |  | To Do | 2022-10-13 | 2022-10-21 | Xiao Lin | Lion | Test Log
| UAT | Test data preparation |  | To Do | 2022-10-20 | 2022-10-21 | Doris | Lion | Test Data
|  | UAT Deployment(IQ and request for RMO) |  | To Do | 2022-10-20 | 2022-10-21 | Doris | Lion | Deployment to UAT Environment
|  | Test case execution |  | To Do | 2022-10-24 | 2022-11-11 | Xiao Lin | Lion | Test Log
| SDLC & Training & KT | SDLC | Requirements Specification. | In Progress | 2022-09-26 | 2022-10-14 | Polina | Lion | Document Signature
|  |  | Design Specification | In Progress | 2022-09-26 | 2022-10-14 | Charles | Lion | Document Signature
|  |  | Solution Review | To Do | 2022-10-11 | 2022-10-11 | Charles | Lion
|  |  | SIT Test Case | In Progress | 2022-10-17 | 2022-10-21 | Xiao Lin | Lion | Document Signature
|  |  | SIT Test Log | To Do | 2022-10-17 | 2022-10-21 | Xiao Lin | Lion | Document Signature
|  |  | UAT Test Case+Test Log | To Do | 2022-10-24 | 2022-11-11 | Xiao Lin | Lion | Document Signature | case+log放在一个文件签掉
|  |  | Requirements Traceibility Matrix | To Do | 2022-10-24 | 2022-11-11 | Xiao Lin,Polina | Lion | Document Signature
|  |  | Deployment Plan | To Do | 2022-10-24 | 2022-11-11 | Charles,Doris | Lion | Document Signature
|  | Amdin Guide |  | To Do | 2022-10-24 | 2022-11-11 | Charles,Doris | AMS | Confluence | 给AMS看的，写在confluence，无签字和PDF
|  | KT to AMS |  | To Do | 2022-10-24 | 2022-11-11 | Charles,Doris,Vicky | AMS |  | AMS 在上线单确认完成
|  | Business User Training |  | To Do | 2022-10-24 | 2022-11-11 | Polina,Vicky | Lion
| Go-Live | IQ preparation |  | To Do | 2022-11-14 | 2022-11-15 | Charles | Lion
|  | Raise request to China RMO |  | To Do | 2022-11-16 | 2022-11-17 | Charles | Lion
|  | Purtora ticket to global RMO |  | To Do | 2022-11-16 | 2022-11-17 | Charles | Lion
|  | IQ review with global RMO |  | To Do | 2022-11-16 | 2022-11-17 | Charles | Lion
|  | Deployment Verification |  | To Do | 2022-11-18 | 2022-11-18 | Charles | Lion
| Hyper Care | Hyper Care support |  | To Do
WeChat Work 研而有信 Reports | Analysis | Business Requirement analysis |  | In Progress | 2022-09-26 | 2022-09-30 | Polina | Lion | Document Review
|  | Lexiang Inbound analysis |  | In Progress | 2022-09-26 | 2022-09-30 | Frank | Lion | Source Data and Node.js Code
|  | Self-Service tech analysis |  | To Do | 2022-09-26 | 2022-09-30 | Charles | Lion | Document Review
| Design | Self-Service POC |  | To Do | 2022-09-26 | 2022-09-30 | Vicky | Lion | POC
|  | Self-Service Design |  | To Do | 2022-09-26 | 2022-09-30 | Vicky | Lion | Draft Design Document
|  | Lexiang Inbound Design |  | To Do | 2022-09-26 | 2022-09-30 | Charles | Lion | Draft Design Document
|  | DWH & DM Design |  | To Do | 2022-09-26 | 2022-09-30 | Charles | Lion | Draft Design Document
| Development | Inbound |  | In Progress | 2022-09-26 | 2022-10-08 | Doris | Charles
|  | Self-Service |  | In Review | 2022-09-26 | 2022-10-08 | Vicky | Charles
|  | DWH & DM |  | In Review | 2022-09-26 | 2022-10-08 | Doris | Charles
| SIT | Test case design |  | In Review | 2022-09-19 | 2022-09-30 | Xiao Lin | Lion
|  | Test data preparation |  | To Do | 2022-10-08 | 2022-10-09 | Doris | Lion
|  | SIT Deployment(IQ and request for RMO) |  | To Do | 2022-10-10 | 2022-10-12 | Doris | Lion
|  | Test case execution |  | To Do | 2022-10-10 | 2022-10-21 | Xiao Lin | Lion
| UAT | Test data preparation |  | To Do | 2022-10-20 | 2022-10-21 | Doris | Lion
|  | UAT Deployment(IQ and request for RMO) |  | To Do | 2022-10-20 | 2022-10-21 | Doris | Lion
|  | Test case execution |  | To Do | 2022-10-27 | 2022-11-11 | Xiao Lin | Lion
| SDLC & Training & KT | SDLC | Requirements Specification. | To Do | 2022-09-26 | 2022-10-14 | Polina | Lion | Document Signature
|  |  | Design Specification | To Do | 2022-09-26 | 2022-10-14 | Charles | Lion | Document Signature
|  |  | Solution Review | To Do | 2022-10-11 | 2022-10-11 | Charles | Lion
|  |  | SIT Test Case | To Do | 2022-10-17 | 2022-10-21 | Xiao Lin | Lion | Document Signature
|  |  | SIT Test Log | To Do | 2022-10-17 | 2022-10-21 | Xiao Lin | Lion | Document Signature
|  |  | UAT Test Case+Test Log | To Do | 2022-10-24 | 2022-11-11 | Xiao Lin | Lion | Document Signature | case+log放在一个文件签掉
|  |  | Requirements Traceibility Matrix | To Do | 2022-10-24 | 2022-11-11 | Xiao Lin,Polina | Lion | Document Signature
|  |  | Deployment Plan | To Do | 2022-10-24 | 2022-11-11 | Charles,Doris | Lion | Document Signature
|  | Amdin Guide |  | To Do | 2022-10-24 | 2022-11-11 | Charles,Doris | AMS | Confluence | 给AMS看的，写在confluence，无签字和PDF
|  | KT to AMS |  | To Do | 2022-10-24 | 2022-11-11 | Charles,Doris,Vicky | AMS |  | AMS 在上线单确认完成
|  | Business User Training |  | To Do | 2022-10-24 | 2022-11-11 | Polina,Vicky | Lion
| Go-Live | IQ preparation |  | To Do | 2022-11-14 | 2022-11-15 | Charles | Lion
|  | Raise request to China RMO |  | To Do | 2022-11-16 | 2022-11-17 | Charles | Lion
|  | Purtora ticket to global RMO |  | To Do | 2022-11-16 | 2022-11-17 | Charles | Lion
|  | IQ review with global RMO |  | To Do | 2022-11-16 | 2022-11-17 | Charles | Lion
|  | Deployment Verification |  | To Do | 2022-11-18 | 2022-11-18 | Charles | Lion
| Hyper Care | Hyper Care support |  | To Do

## POC Plan
2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
Solution Proposal
Proposal Review and Cofirmation
| Environment Access Application | Environment Access Application | Environment Access Application | Environment Access Application
|  | PoC | PoC | PoC Change & Verify | PoC Change & Verify
Analysis | Analysis
| Design | Design
|  |  | Dev | Dev | Dev | Dev
[6 empty] | `SIT |  | `SIT

## POC Plan New
2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10
Solution Proposal
Proposal Review and Cofirmation
| Environment Access Application | Environment Access Application | Environment Access Application | Environment Access Application
|  | PoC | PoC | New solution POC | New solution POC review and confirmation
Analysis | Analysis
| Design | Design
|  |  | Dev | Dev | Dev | Dev
[6 empty] | `SIT |  | `SIT

## CE Phase2 Category Overview (hidden)
Count of Task | 列标签
行标签 | 1. As-Is analysis & Simplification | 2. Technical Design | 3. Dev & UT | 4. SIT | 5. UAT | 6. Go-Live | 7. Parallel Run | 8. Cut Over | 9. Hyper Care | 总计
Data Inbound | 14 | 9 | 6 | 10 | 7 | 9 |  |  | 1 | 56
Data Mart & Outbound | 22 | 8 | 8 | 10 | 7 | 9 | 1 | 9 | 1 | 75
Data Mart Development |  |  | 1 | [6 empty] | 1
Deployment | [5 empty] | 1 |  | 1 |  | 2
Hyper Care support | [8 empty] | 1 | 1
IQ preparation | [5 empty] | 1 |  | 1 |  | 2
IQ review with global RMO | [5 empty] | 1 |  | 1 |  | 2
KT to AMS | [5 empty] | 1 |  | 1 |  | 2
Onboarding form | [5 empty] | 1 |  | 1 |  | 2
OT doc | [5 empty] | 1 |  | 1 |  | 2
Outbound Data Mart model design |  | 1 | [7 empty] | 1
Outbound detail design specification |  | 1 | [7 empty] | 1
Outbound detail design specification review |  | 1 | [7 empty] | 1
Outbound detail design specification sign-of |  | 1 | [7 empty] | 1
Outbound E2E DAG design |  | 1 | [7 empty] | 1
Outbound E2E overall dataflow(high level) |  | 1 | [7 empty] | 1
Outbound E3E overall dataflow(high level) review |  | 1 | [7 empty] | 1
Outbound ETL mapping design |  | 1 | [7 empty] | 1
Outbound interface development |  |  | 7 | [6 empty] | 7
Outbound meta analysis | 9 | [8 empty] | 9
Outbound system business analysis | 13 | [8 empty] | 13
Parallel run testing | [6 empty] | 1 |  |  | 1
Purtora ticket to global RMO | [5 empty] | 1 |  | 1 |  | 2
Raise request to China RMO | [5 empty] | 1 |  | 1 |  | 2
requirement and design KT |  |  |  | 1 | [5 empty] | 1
SDLC doc sign-off | [5 empty] | 1 |  | 1 |  | 2
SIT Approach and plan |  |  |  | 1 | [5 empty] | 1
SIT Approach and plan review |  |  |  | 1 | [5 empty] | 1
SIT Deployment(IQ and request for RMO) |  |  |  | 1 | [5 empty] | 1
SIT Sign-off |  |  |  | 1 | [5 empty] | 1
Test case design |  |  |  | 1 | [5 empty] | 1
Test case execution |  |  |  | 1 | 1 |  |  |  |  | 2
Test case review |  |  |  | 1 | [5 empty] | 1
Test data preparation |  |  |  | 1 | 1 |  |  |  |  | 2
Test log |  |  |  | 1 | 1 |  |  |  |  | 2
UAT Deployment(IQ and request for RMO) |  |  |  |  | 1 |  |  |  |  | 1
UAT Sign-off |  |  |  |  | 1 |  |  |  |  | 1
UAT test case design |  |  |  |  | 1 |  |  |  |  | 1
UAT test case design review |  |  |  |  | 1 |  |  |  |  | 1
Data Mart & Report | 12 | 8 | 4 | 10 | 7 | 9 |  |  | 1 | 51
Teradata Decouple | 6 | 5 | 1 | 10 | 7 | 9 |  |  | 1 | 39
总计 | 54 | 30 | 19 | 40 | 28 | 36 | 1 | 9 | 4 | 221

## CE Phase2 Detail Task Plan_bkp (hidden)
SN | Category | SDLC Phase | Task | sub-task | sub-task description
| Data Inbound | 1. As-Is analysis & Simplification | Inbound interface meta analysis | eMeeting inbound data flow analysis | Inbound name, type, trigger time/condition, loading strategy(incremental/full) , historical data volume, incremental data volume, utilization etc
| Data Inbound | 1. As-Is analysis & Simplification | Inbound interface meta analysis | Digital-Sign in inbound data flow analysis | Inbound name, type, trigger time/condition, loading strategy(incremental/full) , historical data volume, incremental data volume, utilization etc
| Data Inbound | 1. As-Is analysis & Simplification | Inbound interface meta analysis | DFS inbound data flow analysis | Inbound name, validation rule, loading strategy to 3NF, utilization
| Data Inbound | 1. As-Is analysis & Simplification | Inbound interface meta analysis | Inbound interface as-is dataflow | Generate analysis result document
| Data Inbound | 1. As-Is analysis & Simplification | Inbound interface meta analysis | Inbound interface as-is dataflow review | review analysis result with MSD
| Data Inbound | 1. As-Is analysis & Simplification | Inbound system business analysis | eMeeting inbound analysis | inbound business description
| Data Inbound | 1. As-Is analysis & Simplification | Inbound system business analysis | Digital-Sign in inbound analysis | inbound business description
| Data Inbound | 1. As-Is analysis & Simplification | Inbound system business analysis | DFS inbound analysis | inbound business description
| Data Inbound | 1. As-Is analysis & Simplification | Inbound system business analysis | Inbound interface simplification | simplify flag based on analysis and utilization
| Data Inbound | 1. As-Is analysis & Simplification | Inbound system business analysis | Inbound interface simplification review | review simplification result with MSD
| Data Inbound | 1. As-Is analysis & Simplification | Inbound system business analysis | Inbound interface simplification confirm | confirm simplification result with MSD
| Data Inbound | 1. As-Is analysis & Simplification | Inbound system business analysis | Inbound Requirement Specification | generate inbound requirement specification
| Data Inbound | 1. As-Is analysis & Simplification | Inbound system business analysis | Inbound Requirement Specification Review | review inbound requirement specification with MSD
| Data Inbound | 1. As-Is analysis & Simplification | Inbound system business analysis | Inbound requirement specification sign-off
| Data Inbound | 2. Technical Design | HHIE platform development standard introduction | Inbound standard(from db/file/dfs/api) | MSD introduce the HHIE platform development standard
| Data Inbound | 2. Technical Design | Inbound E2E overall dataflow(high level)
| Data Inbound | 2. Technical Design | Inbound E2E overall dataflow(high level) review
| Data Inbound | 2. Technical Design | Inbound E2E dag design
| Data Inbound | 2. Technical Design | Inbound DWH module design
| Data Inbound | 2. Technical Design | Inbound ETL mapping design(Ingestion, Historization, DWH)
| Data Inbound | 2. Technical Design | Inbound historical data initial design
| Data Inbound | 2. Technical Design | Inbound design specification review
| Data Inbound | 2. Technical Design | Inbound design specification sign-off
| Data Inbound | 3. Dev & UT | HHIE platform development learning
| Data Inbound | 3. Dev & UT | Bitbucket folder creation
| Data Inbound | 3. Dev & UT | Inbound development | historical data initial & UT
| Data Inbound | 3. Dev & UT | Inbound development | ingestion & UT
| Data Inbound | 3. Dev & UT | Inbound development | historization(with exref data initial) & UT
| Data Inbound | 3. Dev & UT | Inbound development | DWH(DWH Table DDL,control table DDL and initial) & UT
| Data Inbound | 4. SIT | requirement and design KT
| Data Inbound | 4. SIT | SIT Approach and plan
| Data Inbound | 4. SIT | SIT Approach and plan review
| Data Inbound | 4. SIT | Test case design
| Data Inbound | 4. SIT | Test case review
| Data Inbound | 4. SIT | Test data preparation
| Data Inbound | 4. SIT | SIT Deployment(IQ and request for RMO)
| Data Inbound | 4. SIT | Test case execution
| Data Inbound | 4. SIT | Test log
| Data Inbound | 4. SIT | SIT Sign-off
| Data Inbound | 5. UAT | UAT test case design
| Data Inbound | 5. UAT | UAT test case design review
| Data Inbound | 5. UAT | Test data preparation
| Data Inbound | 5. UAT | UAT Deployment(IQ and request for RMO)
| Data Inbound | 5. UAT | Test case execution
| Data Inbound | 5. UAT | Test log
| Data Inbound | 5. UAT | UAT Sign-off
| Data Inbound | 6. Go-Live | SDLC doc sign-off
| Data Inbound | 6. Go-Live | IQ preparation
| Data Inbound | 6. Go-Live | KT to AMS
| Data Inbound | 6. Go-Live | Raise request to China RMO
| Data Inbound | 6. Go-Live | OT doc
| Data Inbound | 6. Go-Live | Onboarding form
| Data Inbound | 6. Go-Live | Purtora ticket to global RMO
| Data Inbound | 6. Go-Live | IQ review with global RMO
| Data Inbound | 6. Go-Live | Deployment
| Data Inbound | 9. Hyper Care | Hyper Care support
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report business analysis | As-Is report business analysis(BAIKE)
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report business analysis | As-Is report simplification
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report business analysis | As-Is report simplification review
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report business analysis | As-Is report simplification confirm
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report business analysis | report requirement specification
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report business analysis | report requirement specification review
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report business analysis | report requirement sepcification sign-off
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report Meta analysis | As-is report data flow analysis
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report Meta analysis | 48 replica interface analysis(TD2RD)
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report Meta analysis | 48 replica source table refresh logic analysis(TD)
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report Meta analysis | Common model business logic analysis
| Data Mart & Report | 1. As-Is analysis & Simplification | As-Is report Meta analysis | Common model existing QVS logic analysis
| Data Mart & Report | 2. Technical Design | HHIE Qliksense development standard introduction
| Data Mart & Report | 2. Technical Design | Data Mart Overall Design
| Data Mart & Report | 2. Technical Design | Data Mart Overall Design review
| Data Mart & Report | 2. Technical Design | Data Mart Detail Design specification
| Data Mart & Report | 2. Technical Design | Data Mart Detail Design specification review
| Data Mart & Report | 2. Technical Design | Qliksense design specification
| Data Mart & Report | 2. Technical Design | Qliksense design specification review
| Data Mart & Report | 2. Technical Design | Technical design specification sign-off
| Data Mart & Report | 3. Dev & UT | Qliksense development | QVS development & UT
| Data Mart & Report | 3. Dev & UT | Qliksense development | Model development & UT
| Data Mart & Report | 3. Dev & UT | Data Mart Development | Matillion development & UT
| Data Mart & Report | 3. Dev & UT | Data Mart Development | E2E DAG development & UT
| Data Mart & Report | 4. SIT | requirement and design KT
| Data Mart & Report | 4. SIT | SIT Approach and plan
| Data Mart & Report | 4. SIT | SIT Approach and plan review
| Data Mart & Report | 4. SIT | Test case design
| Data Mart & Report | 4. SIT | Test case review
| Data Mart & Report | 4. SIT | Test data preparation
| Data Mart & Report | 4. SIT | SIT Deployment(IQ and request for RMO)
| Data Mart & Report | 4. SIT | Test case execution
| Data Mart & Report | 4. SIT | Test log
| Data Mart & Report | 4. SIT | SIT Sign-off
| Data Mart & Report | 5. UAT | UAT test case design
| Data Mart & Report | 5. UAT | UAT test case design review
| Data Mart & Report | 5. UAT | Test data preparation
| Data Mart & Report | 5. UAT | UAT Deployment(IQ and request for RMO)
| Data Mart & Report | 5. UAT | Test case execution
| Data Mart & Report | 5. UAT | Test log
| Data Mart & Report | 5. UAT | UAT Sign-off
| Data Mart & Report | 6. Go-Live | SDLC doc sign-off
| Data Mart & Report | 6. Go-Live | IQ preparation
| Data Mart & Report | 6. Go-Live | KT to AMS
| Data Mart & Report | 6. Go-Live | Raise request to China RMO
| Data Mart & Report | 6. Go-Live | OT doc
| Data Mart & Report | 6. Go-Live | Onboarding form
| Data Mart & Report | 6. Go-Live | Purtora ticket to global RMO
| Data Mart & Report | 6. Go-Live | IQ review with global RMO
| Data Mart & Report | 6. Go-Live | Deployment
| Data Mart & Report | 9. Hyper Care | Hyper Care support
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound to SFDC CRM business analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound to WordPress business analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound to vchate business analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound to V-invitation 2.0 business analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound to Smart suggestion business analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound to CNAA and exisiting NBX business analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound to O365 BPM business analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound interface simplification
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound interface simplification review
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound interface simplification confirm
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound requirement specification
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound requirement specification review
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound system business analysis | outbound requirement specification sign-off
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound meta analysis | outbound to SFDC CRM as-is data flow analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound meta analysis | outbound to WordPress as-is data flow analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound meta analysis | outbound to vchate as-is data flow analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound meta analysis | outbound to V-invitation 2.0 as-is data flow analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound meta analysis | outbound to Smart suggestion as-is data flow analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound meta analysis | outbound to CNAA as-is data flow analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound meta analysis | outbound to O365 BPM as-is data flow analysis
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound meta analysis | outbound interface as-is data flow
| Data Mart & Outbound | 1. As-Is analysis & Simplification | Outbound meta analysis | outbound interface as-is data flow review
| Data Mart & Outbound | 2. Technical Design | Outbound E2E overall dataflow(high level)
| Data Mart & Outbound | 2. Technical Design | Outbound E3E overall dataflow(high level) review
| Data Mart & Outbound | 2. Technical Design | Outbound Data Mart model design
| Data Mart & Outbound | 2. Technical Design | Outbound ETL mapping design
| Data Mart & Outbound | 2. Technical Design | Outbound E2E DAG design
| Data Mart & Outbound | 2. Technical Design | Outbound detail design specification
| Data Mart & Outbound | 2. Technical Design | Outbound detail design specification review
| Data Mart & Outbound | 2. Technical Design | Outbound detail design specification sign-of
| Data Mart & Outbound | 3. Dev & UT | Data Mart development | DDL and Matillion development
| Data Mart & Outbound | 3. Dev & UT | Outbound interface development | outbound to SFDC CRM(to DI) development & UT
| Data Mart & Outbound | 3. Dev & UT | Outbound interface development | outbound to WordPress development & UT
| Data Mart & Outbound | 3. Dev & UT | Outbound interface development | outbound to vchate development & UT
| Data Mart & Outbound | 3. Dev & UT | Outbound interface development | outbound to V-invitation 2.0 development & UT
| Data Mart & Outbound | 3. Dev & UT | Outbound interface development | outbound to Smart suggestion development & UT
| Data Mart & Outbound | 3. Dev & UT | Outbound interface development | outbound to CNAA development & UT
| Data Mart & Outbound | 3. Dev & UT | Outbound interface development | outbound to O365 BPM development & UT
| Data Mart & Outbound | 4. SIT | requirement and design KT
| Data Mart & Outbound | 4. SIT | SIT Approach and plan
| Data Mart & Outbound | 4. SIT | SIT Approach and plan review
| Data Mart & Outbound | 4. SIT | Test case design
| Data Mart & Outbound | 4. SIT | Test case review
| Data Mart & Outbound | 4. SIT | Test data preparation
| Data Mart & Outbound | 4. SIT | SIT Deployment(IQ and request for RMO)
| Data Mart & Outbound | 4. SIT | Test case execution
| Data Mart & Outbound | 4. SIT | Test log
| Data Mart & Outbound | 4. SIT | SIT Sign-off
| Data Mart & Outbound | 5. UAT | UAT test case design
| Data Mart & Outbound | 5. UAT | UAT test case design review
| Data Mart & Outbound | 5. UAT | Test data preparation
| Data Mart & Outbound | 5. UAT | UAT Deployment(IQ and request for RMO)
| Data Mart & Outbound | 5. UAT | Test case execution
| Data Mart & Outbound | 5. UAT | Test log
| Data Mart & Outbound | 5. UAT | UAT Sign-off
| Data Mart & Outbound | 6. Go-Live | SDLC doc sign-off
| Data Mart & Outbound | 6. Go-Live | IQ preparation
| Data Mart & Outbound | 6. Go-Live | KT to AMS
| Data Mart & Outbound | 6. Go-Live | Raise request to China RMO
| Data Mart & Outbound | 6. Go-Live | OT doc
| Data Mart & Outbound | 6. Go-Live | Onboarding form
| Data Mart & Outbound | 6. Go-Live | Purtora ticket to global RMO
| Data Mart & Outbound | 6. Go-Live | IQ review with global RMO
| Data Mart & Outbound | 6. Go-Live | Deployment
| Data Mart & Outbound | 7. Parallel Run | Parallel run testing
| Data Mart & Outbound | 8. Cut Over | SDLC doc sign-off
| Data Mart & Outbound | 8. Cut Over | IQ preparation
| Data Mart & Outbound | 8. Cut Over | KT to AMS
| Data Mart & Outbound | 8. Cut Over | Raise request to China RMO
| Data Mart & Outbound | 8. Cut Over | OT doc
| Data Mart & Outbound | 8. Cut Over | Onboarding form
| Data Mart & Outbound | 8. Cut Over | Purtora ticket to global RMO
| Data Mart & Outbound | 8. Cut Over | IQ review with global RMO
| Data Mart & Outbound | 8. Cut Over | Deployment
| Data Mart & Outbound | 9. Hyper Care | Hyper Care support
| Teradata Decouple | 1. As-Is analysis & Simplification | Teradata related Meta analysis for CE | Meta for Autosys, informatica, shell, DFS, etc
| Teradata Decouple | 1. As-Is analysis & Simplification | Decouple list review
| Teradata Decouple | 1. As-Is analysis & Simplification | Decouple list confirm
| Teradata Decouple | 1. As-Is analysis & Simplification | Teradata decouple requirement specification
| Teradata Decouple | 1. As-Is analysis & Simplification | Teradata decouple requirement specification review
| Teradata Decouple | 1. As-Is analysis & Simplification | Teradata decouple requirement specification sign-off
| Teradata Decouple | 2. Technical Design | Decouple high level design
| Teradata Decouple | 2. Technical Design | Decouple high level design review
| Teradata Decouple | 2. Technical Design | Decouple detail design specification
| Teradata Decouple | 2. Technical Design | Decouple detail design specification review
| Teradata Decouple | 2. Technical Design | Decouple detail design specification sign-off
| Teradata Decouple | 3. Dev & UT | Decople development | job disable, retire, exisiting file path exchange, etc & UT
| Teradata Decouple | 4. SIT | requirement and design KT
| Teradata Decouple | 4. SIT | SIT Approach and plan
| Teradata Decouple | 4. SIT | SIT Approach and plan review
| Teradata Decouple | 4. SIT | Test case design
| Teradata Decouple | 4. SIT | Test case review
| Teradata Decouple | 4. SIT | Test data preparation
| Teradata Decouple | 4. SIT | SIT Deployment(IQ and request for RMO)
| Teradata Decouple | 4. SIT | Test case execution
| Teradata Decouple | 4. SIT | Test log
| Teradata Decouple | 4. SIT | SIT Sign-off
| Teradata Decouple | 5. UAT | UAT test case design
| Teradata Decouple | 5. UAT | UAT test case design review
| Teradata Decouple | 5. UAT | Test data preparation
| Teradata Decouple | 5. UAT | UAT Deployment(IQ and request for RMO)
| Teradata Decouple | 5. UAT | Test case execution
| Teradata Decouple | 5. UAT | Test log
| Teradata Decouple | 5. UAT | UAT Sign-off
| Teradata Decouple | 6. Go-Live | SDLC doc sign-off
| Teradata Decouple | 6. Go-Live | IQ preparation
| Teradata Decouple | 6. Go-Live | KT to AMS
| Teradata Decouple | 6. Go-Live | Raise request to China RMO
| Teradata Decouple | 6. Go-Live | OT doc
| Teradata Decouple | 6. Go-Live | Onboarding form
| Teradata Decouple | 6. Go-Live | Purtora ticket to global RMO
| Teradata Decouple | 6. Go-Live | IQ review with global RMO
| Teradata Decouple | 6. Go-Live | Deployment
| Teradata Decouple | 9. Hyper Care | Hyper Care support